## JANUARY-JUNE 2021
Dipolog City Water District Procurement Monitoring Report as of January - June 30, 2021
Code (PAP) PR NO. | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conf. | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Delivery/ Accept
COMPLETED PROCUREMENT ACTIVITIES
A001000121 | Commercial | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-07 | n/a | n/a | 2021-01-12 | n/a | 2021-01-13 | 7 CD | 2021-01-15 | General Fund | 24900 | 24900 |  | 14820 | 14820 |  | n/a | n/a | n/a | n/a | 2021-01-07 | n/a | n/a | 2021-01-12 | n/a | 2021-01-15
| Commercial | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-07 | n/a | n/a | 2021-01-12 | n/a | 2021-01-13 | 7 CD | 2021-01-19 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-01-07 | n/a | n/a | 2021-01-12 | n/a | 2021-01-19
A003000321 | Office Supplies | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-07 | n/a | n/a | 2021-01-12 | n/a | 2021-01-13 | 7 CD | 2021-01-14 | General Fund | 3000 | 3000 |  | 1850 | 1850 |  | n/a | n/a | n/a | n/a | 2021-01-07 | n/a | n/a | 2021-01-12 | n/a | 2021-01-14
A004000421 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-21 | n/a | n/a | 2021-01-22 | n/a | 2021-01-29 | 45 CD | 2021-02-02 | General Fund | 543500 | 543500 |  | 502500 | 502500 |  | n/a | n/a | n/a | n/a | 2021-01-21 | n/a | n/a | 2021-01-22 | n/a | 2021-02-02
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-21 | n/a | n/a | 2021-01-22 | n/a | 2021-01-29 | 45 CD | 2021-02-18 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-01-21 | n/a | n/a | 2021-01-22 | n/a | 2021-02-18
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-21 | n/a | n/a | 2021-01-22 | n/a | 2021-01-29 | 45 CD | 2021-03-12 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-01-21 | n/a | n/a | 2021-01-22 | n/a | 2021-03-12
A005000521 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-11 | n/a | n/a | 2021-01-14 | n/a | 2021-01-15 | 7 CD | 2021-01-15 | General Fund | 38680 | 38680 |  | 8321.6 | 8321.6 |  | n/a | n/a | n/a | n/a | 2021-01-11 | n/a | n/a | 2021-01-14 | n/a | 2021-01-15
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-11 | n/a | n/a | 2021-01-14 | n/a | 2021-01-15 | 7 CD | 2021-01-20 | General Fund |  |  |  | 4280 | 4280 |  | n/a | n/a | n/a | n/a | 2021-01-11 | n/a | n/a | 2021-01-14 | n/a | 2021-01-20
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-11 | n/a | n/a | 2021-01-14 | n/a | 2021-01-15 | 7 CD | 2021-01-25 | General Fund |  |  |  | 1138.8 | 1138.8 |  | n/a | n/a | n/a | n/a | 2021-01-11 | n/a | n/a | 2021-01-14 | n/a | 2021-01-25
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-11 | n/a | n/a | 2021-01-14 | n/a | 2021-01-19 | 30 CD | 2021-04-16 | General Fund |  |  |  | 22500 | 22500 |  | n/a | n/a | n/a | n/a | 2021-01-11 | n/a | n/a | 2021-01-14 | n/a | 2021-04-16
A006000621 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-19 | n/a | n/a | 2021-01-22 | n/a | 2021-01-22 | 7 CD | 2021-02-18 | General Fund | 45000 | 45000 |  | 43800 | 43800 |  | n/a | n/a | n/a | n/a | 2021-01-19 | n/a | n/a | 2021-01-22 | n/a | 2021-02-18
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-19 | n/a | n/a | 2021-01-22 | n/a | 2021-01-22 | 7 CD | 2021-03-02 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-01-19 | n/a | n/a | 2021-01-22 | n/a | 2021-03-02
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-19 | n/a | n/a | 2021-01-22 | n/a | 2021-01-22 | 7 CD | 2021-04-20 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-01-19 | n/a | n/a | 2021-01-22 | n/a | 2021-04-20
A007000721 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-22 | n/a | n/a | 2021-01-27 | n/a | 2021-02-02 | 7 CD | 2021-02-15 | General Fund | 12500 | 12500 |  | 12000 | 12000 |  | n/a | n/a | n/a | n/a | 2021-01-22 | n/a | n/a | 2021-01-27 | n/a | 2021-02-15
A012001221 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-07 | n/a | 2021-01-07 | 1 CD | 2021-01-13 | General Fund | 6990 | 6990 |  | 6990 | 6990 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-07 | n/a | 2021-01-13
A014001421 | Office Building Maintenance | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-08 | n/a | n/a | 2021-01-08 | n/a | 2021-01-12 | 7 CD | 2021-01-12 | General Fund | 24000 | 24000 |  | 22900 | 22900 |  | n/a | n/a | n/a | n/a | 2021-01-08 | n/a | n/a | 2021-01-08 | n/a | 2021-01-12
A015001521 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-13 | n/a | 2021-01-13 | 1 CD | 2021-01-15 | General Fund | 1630.14 | 1630.14 |  | 1630.14 | 1630.14 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-13 | n/a | 2021-01-15
A016001621 | Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-28 | n/a | n/a | 2021-02-03 | n/a | 2021-02-08 | 7 CD | 2021-02-10 | General Fund | 305400 | 305400 |  | 236650 | 236650 |  | n/a | n/a | n/a | n/a | 2021-01-28 | n/a | n/a | 2021-02-03 | n/a | 2021-02-10
| Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-28 | n/a | n/a | 2021-02-03 | n/a | 2021-02-08 | 7 CD | 2021-02-22 | General Fund |  |  |  | 23000 | 23000 |  | n/a | n/a | n/a | n/a | 2021-01-28 | n/a | n/a | 2021-02-03 | n/a | 2021-02-22
A017001721 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-12 | n/a | 2021-01-12 | 1 CD | 2021-01-14 | General Fund | 1100 | 1100 |  | 1100 | 1100 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-12 | n/a | 2021-01-14
A018001821 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-12 | n/a | 2021-01-12 | 1 CD | 2021-01-14 | General Fund | 1500 | 1500 |  | 1500 | 1500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-12 | n/a | 2021-01-14
A020002021 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-27 | n/a | n/a | 2021-01-27 | n/a | 2021-01-27 | 7 CD | 2021-01-27 | General Fund | 69500 | 69500 |  | 15400 | 15400 |  | n/a | n/a | n/a | n/a | 2021-01-27 | n/a | n/a | 2021-01-27 | n/a | 2021-01-27
| Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-27 | n/a | n/a | 2021-01-27 | n/a | 2021-01-27 | 7 CD | 2021-01-27 | General Fund |  |  |  | 32644 | 32644 |  | n/a | n/a | n/a | n/a | 2021-01-27 | n/a | n/a | 2021-01-27 | n/a | 2021-01-27
| Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-27 | n/a | n/a | 2021-01-27 | n/a | 2021-02-02 | 7 CD | 2021-02-02 | General Fund |  |  |  | 1185 | 1185 |  | n/a | n/a | n/a | n/a | 2021-01-27 | n/a | n/a | 2021-01-27 | n/a | 2021-02-02
A021002121 | Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-25 | n/a | n/a | 2021-01-25 | n/a | 2021-01-20 | 7 CD | 2021-01-20 | General Fund | 60512 | 60512 |  | 24502 | 24502 |  | n/a | n/a | n/a | n/a | 2021-01-25 | n/a | n/a | 2021-01-25 | n/a | 2021-01-20
| Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-25 | n/a | n/a | 2021-01-25 | n/a | 2021-01-19 | 7 CD | 2021-01-20 | General Fund |  |  |  | 31836 | 31836 |  | n/a | n/a | n/a | n/a | 2021-01-25 | n/a | n/a | 2021-01-25 | n/a | 2021-01-20
A023002321 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-20 | n/a | n/a | 2021-01-26 | n/a | 2021-01-29 | 7 CD | 2021-02-03 | General Fund | 22400 | 22400 |  | 10706 | 10706 |  | n/a | n/a | n/a | n/a | 2021-01-20 | n/a | n/a | 2021-01-26 | n/a | 2021-02-03
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-20 | n/a | n/a | 2021-01-26 | n/a | 2021-02-05 | 7 CD | 2021-02-05 | General Fund |  |  |  | 8290 | 8290 |  | n/a | n/a | n/a | n/a | 2021-01-20 | n/a | n/a | 2021-01-26 | n/a | 2021-02-05
A024002421 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-20 | n/a | n/a | 2021-01-22 | n/a | 2021-01-29 | 7 CD | 2021-02-02 | General Fund | 9000 | 9000 |  | 8900 | 8900 |  | n/a | n/a | n/a | n/a | 2021-01-20 | n/a | n/a | 2021-01-22 | n/a | 2021-02-02
A025002521 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-19 | n/a | 2021-01-19 | 1 CD | 2021-01-22 | General Fund | 6488.87 | 6488.87 |  | 6488.87 | 6488.87 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-19 | n/a | 2021-01-22
A026002621 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-21 | n/a | 2021-01-21 | 1 CD | 2021-01-28 | General Fund | 9411.65 | 9411.65 |  | 9411.65 | 9411.65 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-21 | n/a | 2021-01-28
A027002721 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-22 | n/a | n/a | 2021-01-27 | n/a | 2021-01-29 | 7 CD | 2021-02-03 | General Fund | 10000 | 10000 |  | 8300 | 8300 |  | n/a | n/a | n/a | n/a | 2021-01-22 | n/a | n/a | 2021-01-27 | n/a | 2021-02-03
A028002821 | Pumping Station | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-22 | n/a | 2021-01-22 | 1 CD | 2021-01-28 | General Fund | 780 | 780 |  | 780 | 780 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-22 | n/a | 2021-01-28
A029002921 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-22 | n/a | 2021-01-22 | 1 CD | 2021-01-28 | General Fund | 1050 | 1050 |  | 1050 | 1050 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-22 | n/a | 2021-01-28
A030003021 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-22 | n/a | 2021-01-22 | 1 CD | 2021-01-28 | General Fund | 1400 | 1400 |  | 1400 | 1400 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-22 | n/a | 2021-01-28
A031003121 | Office Supplies | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-22 | n/a | n/a | 2021-01-25 | n/a | 2021-01-25 | 60 CD | 2021-03-19 | General Fund | 20000 | 20000 |  | 9000 | 9000 |  | n/a | n/a | n/a | n/a | 2021-01-22 | n/a | n/a | 2021-01-25 | n/a | 2021-03-19
A032003221 | Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-28 | n/a | n/a | 2021-02-03 | n/a | 2021-02-03 | 30 CD | 2021-02-26 | General Fund | 126000 | 126000 |  | 123024 | 123024 |  | n/a | n/a | n/a | n/a | 2021-01-28 | n/a | n/a | 2021-02-03 | n/a | 2021-02-26
A033003321 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-22 | n/a | n/a | 2021-01-27 | n/a | 2021-01-29 | 7 CD | 2021-02-02 | General Fund | 15000 | 15000 |  | 6000 | 6000 |  | n/a | n/a | n/a | n/a | 2021-01-22 | n/a | n/a | 2021-01-27 | n/a | 2021-02-02
A034003421 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-26 | n/a | n/a | 2021-01-27 | n/a | 2021-01-29 | 7 CD | 2021-02-02 | General Fund | 18400 | 18400 |  | 212 | 212 |  | n/a | n/a | n/a | n/a | 2021-01-26 | n/a | n/a | 2021-01-27 | n/a | 2021-02-02
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-26 | n/a | n/a | 2021-01-27 | n/a | 2021-01-29 | 7 CD | 2021-02-01 | General Fund |  |  |  | 11400 | 11400 |  | n/a | n/a | n/a | n/a | 2021-01-26 | n/a | n/a | 2021-01-27 | n/a | 2021-02-01
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-01-26 | n/a | n/a | 2021-01-27 | n/a | 1906-08-16 | 7 CD | 2021-02-03 | General Fund |  |  |  | 2420 | 2420 |  | n/a | n/a | n/a | n/a | 2021-01-26 | n/a | n/a | 2021-01-27 | n/a | 2021-02-03
A035003521 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-02 | n/a | n/a | 2021-02-04 | n/a | 2021-02-04 | 7 CD | 2021-02-11 | General Fund | 95600 | 95600 |  | 30754 | 30754 |  | n/a | n/a | n/a | n/a | 2021-02-02 | n/a | n/a | 2021-02-04 | n/a | 2021-02-11
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-02 | n/a | n/a | 2021-02-04 | n/a | 2021-02-08 | 7 CD | 2021-02-11 | General Fund |  |  |  | 9168 | 9168 |  | n/a | n/a | n/a | n/a | 2021-02-02 | n/a | n/a | 2021-02-04 | n/a | 2021-02-11
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-02 | n/a | n/a | 2021-02-04 | n/a | 2021-02-08 | 7 CD | 2021-02-11 | General Fund |  |  |  | 5820 | 5820 |  | n/a | n/a | n/a | n/a | 2021-02-02 | n/a | n/a | 2021-02-04 | n/a | 2021-02-11
A036003621 | Office Supplies | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-09 | n/a | 2021-02-10 | 7 CD | 2021-02-15 | General Fund | 11280 | 11280 |  | 291.5 | 291.5 |  | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-09 | n/a | 2021-02-15
| Office Supplies | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-09 | n/a | 2021-02-16 | 7 CD | 2021-02-22 | General Fund |  |  |  | 2075 | 2075 |  | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-09 | n/a | 2021-02-22
| Office Supplies | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-09 | n/a | 2021-02-11 | 7 CD | 2021-02-26 | General Fund |  |  |  | 4440 | 4440 |  | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-09 | n/a | 2021-02-26
A037003721 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-08 | 7 CD | 2021-02-09 | General Fund | 14440 | 14440 |  | 8572 | 8572 |  | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-09
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-09 | 7 CD | 2021-02-11 | General Fund |  |  |  | 600 | 600 |  | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-11
A038003821 | Three Months Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-12 | n/a | n/a | 2021-02-16 | n/a | 2021-02-17 | 30 CD | 2021-03-12 | General Fund | 280800 | 280800 |  | 231177.5 | 231177.5 |  | n/a | n/a | n/a | n/a | 2021-02-12 | n/a | n/a | 2021-02-16 | n/a | 2021-03-12
| Three Months Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-12 | n/a | n/a | 2021-02-16 | n/a | 2021-02-17 | 30 CD | 2021-03-12 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-02-12 | n/a | n/a | 2021-02-16 | n/a | 2021-03-12
A039003921 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-04 | n/a | n/a | 2021-02-09 | n/a | 2021-02-11 | 7 CD | 2021-02-11 | General Fund | 7500 | 7500 |  | 6800 | 6800 |  | n/a | n/a | n/a | n/a | 2021-02-04 | n/a | n/a | 2021-02-09 | n/a | 2021-02-11
A040004021 | Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-04 | n/a | n/a | 2021-02-09 | n/a | 2021-02-11 | 7 CD | 2021-02-15 | General Fund | 10000 | 10000 |  | 6800 | 6800 |  | n/a | n/a | n/a | n/a | 2021-02-04 | n/a | n/a | 2021-02-09 | n/a | 2021-02-15
A041004121 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-27 | n/a | 2021-01-27 | 1 CD | 2021-02-02 | General Fund | 23377.37 | 23377.37 |  | 23377.37 | 23377.37 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-27 | n/a | 2021-02-02
A042004221 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-02 | n/a | n/a | 2021-02-05 | n/a | 2021-02-05 | 30 CD | 2021-03-09 | General Fund | 900000 | 900000 |  | 879000 | 879000 |  | n/a | n/a | n/a | n/a | 2021-02-02 | n/a | n/a | 2021-02-05 | n/a | 2021-03-09
A043004321 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-09 | 7 CD | 2021-02-09 | General Fund | 32500 | 32500 |  | 23400 | 23400 |  | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-09
A044004421 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-05 | n/a | 2021-03-10 | 7 CD | 2021-03-30 | General Fund | 175000 | 175000 |  | 146900 | 146900 |  | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-05 | n/a | 2021-03-30
A045004521 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-10 | n/a | n/a | 2021-02-11 | n/a | 2021-02-17 | 30 CD | 2021-02-17 | General Fund | 205000 | 205000 |  | 61000 | 61000 |  | n/a | n/a | n/a | n/a | 2021-02-10 | n/a | n/a | 2021-02-11 | n/a | 2021-02-17
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-10 | n/a | n/a | 2021-02-22 | n/a | 2021-02-22 | 7 CD | 2021-02-26 | General Fund |  |  |  | 99900 | 99900 |  | n/a | n/a | n/a | n/a | 2021-02-10 | n/a | n/a | 2021-02-22 | n/a | 2021-02-26
A049004921 | Vehicle and heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-01 | n/a | 2021-02-01 | 1 CD | 2021-02-01 | General Fund | 3200 | 3200 |  | 3200 | 3200 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-01 | n/a | 2021-02-01
A050005021 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-27 | n/a | 2021-01-27 | 1 CD | 2021-02-11 | General Fund | 4030 | 4030 |  | 2530 | 2530 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-27 | n/a | 2021-02-11
A053005321 | Well 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-01 | n/a | n/a | 2021-03-04 | n/a | 2021-03-09 | 30 CD | 2021-03-12 | General Fund | 311000 | 311000 |  | 52000 | 52000 |  | n/a | n/a | n/a | n/a | 2021-03-01 | n/a | n/a | 2021-03-04 | n/a | 2021-03-12
| Well 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-01 | n/a | n/a | 2021-03-04 | n/a | 2021-03-10 | 30 CD | 2021-04-07 | General Fund |  |  |  | 223755 | 223755 |  | n/a | n/a | n/a | n/a | 2021-03-01 | n/a | n/a | 2021-03-04 | n/a | 2021-04-07
A054005421 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-09 | 7 CD | 2021-02-16 | General Fund | 35200 | 35200 |  | 6000 | 6000 |  | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-16
A058005821 | Well 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-04 | n/a | n/a | 2021-02-09 | n/a | 2021-02-24 | 7 CD | 2021-02-24 | General Fund | 8288.51 | 8288.51 |  | 8288.51 | 8288.51 |  | n/a | n/a | n/a | n/a | 2021-02-04 | n/a | n/a | 2021-02-09 | n/a | 2021-02-24
A060006021 | NST | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-04 | n/a | n/a | 2021-02-09 | n/a | 2021-02-11 | 7 CD | 2021-02-22 | General Fund | 4450 | 4450 |  | 2945 | 2945 |  | n/a | n/a | n/a | n/a | 2021-02-04 | n/a | n/a | 2021-02-09 | n/a | 2021-02-22
A062006221 | Commercial | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-08 | 7 CD | 2021-02-15 | General Fund | 8800 | 8800 |  | 1876 | 1876 |  | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-15
| Commercial | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-08 | 7 CD | 2021-02-15 | General Fund |  |  |  | 4700 | 4700 |  | n/a | n/a | n/a | n/a | 2021-02-01 | n/a | n/a | 2021-02-04 | n/a | 2021-02-15
A063006321 | Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-10 | n/a | n/a | 2021-02-15 | n/a | 2021-02-17 | 30 CD | 2021-02-18 | General Fund | 195800 | 195800 |  | 625 | 625 |  | n/a | n/a | n/a | n/a | 2021-02-10 | n/a | n/a | 2021-02-15 | n/a | 2021-02-18
| Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-10 | n/a | n/a | 2021-02-15 | n/a | 2021-02-11 | 7 CD | 2021-02-22 | General Fund |  |  |  | 23500 | 23500 |  | n/a | n/a | n/a | n/a | 2021-02-10 | n/a | n/a | 2021-02-15 | n/a | 2021-02-22
| Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-10 | n/a | n/a | 2021-02-15 | n/a | 2021-03-01 | 30 CD | 2021-03-02 | General Fund |  |  |  | 89563.5 | 89563.5 |  | n/a | n/a | n/a | n/a | 2021-02-10 | n/a | n/a | 2021-02-15 | n/a | 2021-03-02
A064006421 | Office Building Maintenance | Procurement | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-27 | n/a | 2021-01-27 | 1 CD | 2021-02-03 | General Fund | 7500 | 7500 |  | 7500 | 7500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-01-27 | n/a | 2021-02-03
A066006621 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-05 | n/a | n/a | 2021-02-09 | n/a | 2021-02-10 | 7 CD | 2021-02-11 | General Fund | 23500 | 23500 |  | 3154 | 3154 |  | n/a | n/a | n/a | n/a | 2021-02-05 | n/a | n/a | 2021-02-09 | n/a | 2021-02-11
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-05 | n/a | n/a | 2021-02-09 | n/a | 2021-02-11 | 7 CD | 2021-02-19 | General Fund |  |  |  | 14500 | 14500 |  | n/a | n/a | n/a | n/a | 2021-02-05 | n/a | n/a | 2021-02-09 | n/a | 2021-02-19
A067006721 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-02 | n/a | 2021-02-02 | 7 CD | 2021-02-04 | General Fund | 76550.67 | 76550.67 |  | 76550.67 | 76550.67 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-02 | n/a | 2021-02-04
A070007021 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-09 | n/a | 2021-02-09 | 1 CD | 2021-02-10 | General Fund | 150 | 150 |  | 150 | 150 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-09 | n/a | 2021-02-10
A073007321 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-16 | n/a | n/a | 2021-02-17 | n/a | 2021-02-17 | 7 CD | 2021-03-02 | General Fund | 78500 | 78500 |  | 3220 | 3220 |  | n/a | n/a | n/a | n/a | 2021-02-16 | n/a | n/a | 2021-02-17 | n/a | 2021-03-02
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-16 | n/a | n/a | 2021-02-17 | n/a | 2021-03-04 | 7 CD | 2021-03-04 | General Fund |  |  |  | 37600 | 37600 |  | n/a | n/a | n/a | n/a | 2021-02-16 | n/a | n/a | 2021-02-17 | n/a | 2021-03-04
A077007721 | vehicle and heavy equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-02 | n/a | 2021-02-02 | 1 CD | 2021-02-09 | General Fund | 2800 | 2800 |  | 2800 | 2800 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-02 | n/a | 2021-02-09
A078007821 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-02 | n/a | 2021-02-02 | 1 CD | 2021-02-09 | General Fund | 1800 | 1800 |  | 1800 | 1800 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-02 | n/a | 2021-02-09
A079007921 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-03-02 | n/a | 2021-03-03 | 7 CD | 2021-03-10 | General Fund | 186600 | 186600 |  | 3550 | 3550 |  | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-03-02 | n/a | 2021-03-10
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-04-21 | n/a | 2021-04-26 | 7 CD | 2021-06-24 | General Fund |  |  |  | 1900 | 1900 |  | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-04-21 | n/a | 2021-06-24
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-03-02 | n/a | 2021-03-09 | 7 CD | 2021-03-05 | General Fund |  |  |  | 61550 | 61550 |  | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-03-02 | n/a | 2021-03-09 | 7 CD | 2021-05-25 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-03-02 | n/a | 2021-05-25
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-03-02 | n/a | 2021-03-03 | 7 CD | 2021-03-09 | General Fund |  |  |  | 260 | 260 |  | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-03-02 | n/a | 2021-03-09
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-04-21 | n/a | 2021-04-26 | 7 CD | 2021-04-26 | General Fund |  |  |  | 6800 | 6800 |  | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-04-21 | n/a | 2021-04-26
A080008021 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-02 | n/a | 2021-02-02 | 7 CD | 2021-02-16 | General Fund | 2140 | 2140 |  | 2140 | 2140 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-02 | n/a | 2021-02-16
A081008121 | Office Supplies | Procurement | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-11 | n/a | 2021-02-11 | 7 CD | 2021-03-30 | General Fund | 152000 | 152000 |  | 141100 | 141100 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-11 | n/a | 2021-03-30
A083008321 | Laboratory | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-18 | n/a | n/a | 2021-02-22 | n/a | 2021-02-23 | 7 CD | 2021-02-23 | General Fund | 5550 | 5550 |  | 1832 | 1832 |  | n/a | n/a | n/a | n/a | 2021-02-18 | n/a | n/a | 2021-02-22 | n/a | 2021-02-23
| Laboratory | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-18 | n/a | n/a | 2021-02-22 | n/a | 2021-02-24 | 7 CD | 2021-03-04 | General Fund |  |  |  | 1000 | 1000 |  | n/a | n/a | n/a | n/a | 2021-02-18 | n/a | n/a | 2021-02-22 | n/a | 2021-03-04
B001008021 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-02 | n/a | 2021-03-02 | 7 CD | 2021-03-08 | General Fund | 9000 | 9000 |  | 3500 | 3500 |  | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-02 | n/a | 2021-03-08
B002008121 | Septage | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-08 | n/a | n/a | 2021-02-09 | n/a | 2021-02-10 | 7 CD | 2021-02-11 | General Fund | 10100 | 10100 |  | 2030.85 | 2030.85 |  | n/a | n/a | n/a | n/a | 2021-02-08 | n/a | n/a | 2021-02-09 | n/a | 2021-02-11
| Septage | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-08 | n/a | n/a | 2021-02-09 | n/a | 2021-02-11 | 7 CD | 2021-03-12 | General Fund |  |  |  | 370 | 370 |  | n/a | n/a | n/a | n/a | 2021-02-08 | n/a | n/a | 2021-02-09 | n/a | 2021-03-12
| Septage | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-08 | n/a | n/a | 2021-02-09 | n/a | 2021-02-11 | 7 CD | 2021-02-15 | General Fund |  |  |  | 5705 | 5705 |  | n/a | n/a | n/a | n/a | 2021-02-08 | n/a | n/a | 2021-02-09 | n/a | 2021-02-15
B004008421 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-18 | n/a | n/a | 2021-02-22 | n/a | 2021-02-24 | 7 CD | 2021-02-26 | General Fund | 12500 | 12500 |  | 10400 | 10400 |  | n/a | n/a | n/a | n/a | 2021-02-18 | n/a | n/a | 2021-02-22 | n/a | 2021-02-26
B005008621 | Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-02-26 | 7 CD | 2021-03-01 | General Fund | 212500 | 212500 |  | 188750 | 188750 |  | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-03-01
B007008821 | Office Supply | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-09 | n/a | n/a | 2021-02-10 | n/a | 2021-02-17 | 7 CD | 2021-02-26 | General Fund | 14000 | 14000 |  | 12750 | 12750 |  | n/a | n/a | n/a | n/a | 2021-02-09 | n/a | n/a | 2021-02-10 | n/a | 2021-02-26
B008008921 | Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-11 | n/a | n/a | 2021-02-16 | n/a | 2021-02-18 | 7 CD | 2021-02-19 | General Fund | 11570 | 11570 |  | 6591.4 | 6591.4 |  | n/a | n/a | n/a | n/a | 2021-02-11 | n/a | n/a | 2021-02-16 | n/a | 2021-02-19
| Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-11 | n/a | n/a | 2021-02-16 | n/a | 2021-02-17 | 7 CD | 2021-02-19 | General Fund |  |  |  | 2550 | 2550 |  | n/a | n/a | n/a | n/a | 2021-02-11 | n/a | n/a | 2021-02-16 | n/a | 2021-02-19
B012009321 | WELL 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-09 | n/a | 2021-03-12 | 7 CD | 2021-03-17 | General Fund | 223200 | 223200 |  | 1161.9 | 1161.9 |  | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-09 | n/a | 2021-03-17
| WELL 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-09 | n/a | 2021-03-12 | 7 CD | 2021-03-15 | General Fund |  |  |  | 16570 | 16570 |  | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-09 | n/a | 2021-03-15
| WELL 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-09 | n/a | 2021-03-16 | 7 CD | 2021-03-22 | General Fund |  |  |  | 20249.25 | 20249.25 |  | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-09 | n/a | 2021-03-22
| WELL 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-29 | n/a | 2021-04-06 | 7 CD | 2021-04-12 | General Fund |  |  |  | 925 | 925 |  | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-29 | n/a | 2021-04-12
B013009421 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-17 | n/a | 2021-02-17 | 7 CD | 2021-03-02 | General Fund | 18000 | 18000 |  | 8800 | 8800 |  | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-17 | n/a | 2021-03-02
B014009521 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-17 | n/a | 2021-02-17 | 7 CD | 2021-03-02 | General Fund | 14000 | 14000 |  | 7700 | 7700 |  | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-17 | n/a | 2021-03-02
B015009621 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-17 | n/a | 2021-02-17 | 7 CD | 2021-03-02 | General Fund | 9800 | 9800 |  | 4700 | 4700 |  | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-17 | n/a | 2021-03-02
B016009721 | Office Building Maintenance | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-09 | n/a | n/a | 2021-02-16 | n/a | 2021-02-16 | 7 CD | 2021-02-26 | General Fund | 3500 | 3500 |  | 3500 | 3500 |  | n/a | n/a | n/a | n/a | 2021-02-09 | n/a | n/a | 2021-02-16 | n/a | 2021-02-26
B018009921 | Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-23 | 7 CD | 2021-03-24 | General Fund | 44540 | 44540 |  | 8940 | 8940 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-24
| Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-23 | 7 CD | 2021-03-26 | General Fund |  |  |  | 1700 | 1700 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-26
| Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-23 | 7 CD | 2021-03-29 | General Fund |  |  |  | 4200 | 4200 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-29
| Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-23 | 7 CD | 2021-06-24 | General Fund |  |  |  | 4200 | 4200 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-06-24
| Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-23 | 7 CD | 2021-03-30 | General Fund |  |  |  | 11180 | 11180 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-30
B021010221 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-18 | n/a | 1901-08-22 | 7 CD | 2021-02-24 | General Fund | 35500 | 35500 |  | 600 | 600 |  | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-18 | n/a | 2021-02-24
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-18 | n/a | 2021-04-13 | 7 CD | 2021-04-13 | General Fund |  |  |  | 20033.25 | 20033.25 |  | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-18 | n/a | 2021-04-13
B022010321 | Office Supply | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-16 | n/a | 2021-02-17 | 7 CD | 2021-02-23 | General Fund | 2500 | 2500 |  | 875 | 875 |  | n/a | n/a | n/a | n/a | 2021-02-15 | n/a | n/a | 2021-02-16 | n/a | 2021-02-23
B023010421 | Matunog Gulayon | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-03-01 | 30 CD | 2021-03-04 | General Fund | 144000 | 144000 |  | 28136 | 28136 |  | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-03-04
| Matunog Gulayon | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-03-01 | 30 CD | 2021-03-02 | General Fund |  |  |  | 44781.75 | 44781.75 |  | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-03-02
| Matunog Gulayon | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-03-02 | 60 CD | 2021-03-26 | General Fund |  |  |  | 19785.5 | 19785.5 |  | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-03-26
B024010521 | Kalambuan Sta. Filomena | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-03-01 | 30 CD | 2021-03-04 | General Fund | 122500 | 122500 |  | 24724 | 24724 |  | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-03-04
| Kalambuan Sta. Filomena | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-03-02 | 60 CD | 2021-03-26 | General Fund |  |  |  | 19785.5 | 19785.5 |  | n/a | n/a | n/a | n/a | 2021-02-23 | n/a | n/a | 2021-02-24 | n/a | 2021-03-26
B025010721 | Pumping Station | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-10 | n/a | 2021-02-10 | 7 CD | 2021-02-16 | General Fund | 300 | 300 |  | 243 | 243 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-10 | n/a | 2021-02-16
B026010821 | Office Supply | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-16 | n/a | n/a | 2021-02-17 | n/a | 2021-02-26 | 7 CD | 2021-02-26 | General Fund | 1500 | 1500 |  | 1332.3 | 1332.3 |  | n/a | n/a | n/a | n/a | 2021-02-16 | n/a | n/a | 2021-02-17 | n/a | 2021-02-26
B027010921 | Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-18 | n/a | n/a | 2021-02-23 | n/a | 2021-02-23 | 7 CD | 2021-02-24 | General Fund | 33300 | 33300 |  | 450 | 450 |  | n/a | n/a | n/a | n/a | 2021-02-18 | n/a | n/a | 2021-02-23 | n/a | 2021-02-24
| Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-18 | n/a | n/a | 2021-02-22 | n/a | 2021-02-24 | 7 CD | 2021-03-24 | General Fund |  |  |  | 25450 | 25450 |  | n/a | n/a | n/a | n/a | 2021-02-18 | n/a | n/a | 2021-02-22 | n/a | 2021-03-24
B029011221 | Vehicle and Maintenance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-08 | n/a | 2021-03-08 | 7 CD | 2021-03-19 | General Fund | 1260 | 1260 |  | 1260 | 1260 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-08 | n/a | 2021-03-19
B030011321 | Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-03 | n/a | 2021-03-03 | 30 CD | 2021-03-02 | General Fund | 525000 | 525000 |  | 425880 | 425880 |  | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-03 | n/a | 2021-03-02
| Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-03 | n/a | 2021-03-03 | 30 CD | 2021-03-15 | General Fund |  |  |  | 425880 | 425880 |  | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-03 | n/a | 2021-03-15
B032011521 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 7 CD | 2021-03-05 | General Fund | 49540 | 49540 |  | 18728 | 18728 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05
| Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-16 | n/a | 2021-03-19 | 7 CD | 2021-03-23 | General Fund |  |  |  | 4500 | 4500 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-16 | n/a | 2021-03-23
| Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 7 CD | 2021-03-09 | General Fund |  |  |  | 638 | 638 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-09
| Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-02 | 7 CD | 2021-03-10 | General Fund |  |  |  | 6010 | 6010 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-10
B033011621 | Office Supply | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-22 | n/a | n/a | 2021-03-02 | n/a | 2021-03-02 | 7 CD | 2021-03-12 | General Fund | 21210 | 21210 |  | 4680 | 4680 |  | n/a | n/a | n/a | n/a | 2021-02-22 | n/a | n/a | 2021-03-02 | n/a | 2021-03-12
| Office Supply | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-22 | n/a | n/a | 2021-03-02 | n/a | 2021-03-02 | 7 CD | 2021-03-19 | General Fund |  |  |  | 4680 | 4680 |  | n/a | n/a | n/a | n/a | 2021-02-22 | n/a | n/a | 2021-03-02 | n/a | 2021-03-19
| Office Supply | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-22 | n/a | n/a | 2021-03-02 | n/a | 2021-03-02 | 7 CD | 2021-03-12 | General Fund |  |  |  | 10955 | 10955 |  | n/a | n/a | n/a | n/a | 2021-02-22 | n/a | n/a | 2021-03-02 | n/a | 2021-03-12
B035011821 | ACE | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-03-08 | n/a | 2021-03-10 | 30 CD | 2021-03-16 | General Fund | 150600 | 150600 |  | 41777.76 | 41777.76 |  | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-03-08 | n/a | 2021-03-16
| ACE | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-03-08 | n/a | 2021-03-10 | 30 CD | 2021-03-26 | General Fund |  |  |  | 27336.16 | 27336.16 |  | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-03-08 | n/a | 2021-03-26
| ACE | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-03-08 | n/a | 2021-03-10 | 30 CD | 2021-05-04 | General Fund |  |  |  | 27336.16 | 27336.16 |  | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-03-08 | n/a | 2021-05-04
| ACE | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-03-08 | n/a | 2021-03-08 | 60 CD | 2021-04-07 | General Fund |  |  |  | 23531.2 | 23531.2 |  | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-03-08 | n/a | 2021-04-07
| ACE | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-04-12 | n/a | 2021-04-15 | 30 CD | 2021-04-26 | General Fund |  |  |  | 2000 | 2000 |  | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-04-12 | n/a | 2021-04-26
B037012021 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-04 | n/a | 2021-03-09 | 7 CD | 2021-03-30 | General Fund | 1500 | 1500 |  | 1000 | 1000 |  | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-04 | n/a | 2021-03-30
B038012121 | Office Building Maintenance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-17 | n/a | 2021-02-17 | 1 CD | 2021-02-24 | General Fund | 10472 | 10472 |  | 10472 | 10472 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-17 | n/a | 2021-02-24
B039012221 | Office Extension | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-19 | n/a | n/a | 2021-02-22 | n/a | 2021-03-05 | 7 CD | 2021-03-05 | General Fund | 14750 | 14750 |  | 13830 | 13830 |  | n/a | n/a | n/a | n/a | 2021-02-19 | n/a | n/a | 2021-02-22 | n/a | 2021-03-05
B041012421 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-22 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 7 CD | 2021-03-05 | General Fund | 4800 | 4800 |  | 4500 | 4500 |  | n/a | n/a | n/a | n/a | 2021-02-22 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05
B042012521 | Office Supply | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-15 | 7 CD | 2021-03-15 | General Fund | 4500 | 4500 |  | 780 | 780 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-15
| Office Supply | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-22 | 7 CD | 2021-03-22 | General Fund |  |  |  | 2475 | 2475 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-22
B043012621 | Forest Park | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 7 CD | 2021-03-09 | General Fund | 34150 | 34150 |  | 15400 | 15400 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-09
| Forest Park | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 7 CD | 2021-03-26 | General Fund |  |  |  | 15400 | 15400 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-26
| Forest Park | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 7 CD | 2021-03-09 | General Fund |  |  |  | 8400 | 8400 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-09
| Forest Park | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 7 CD | 2021-03-10 | General Fund |  |  |  | 1975 | 1975 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-10
B044012721 | Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-04 | n/a | 2021-03-10 | 7 CD | 2021-03-12 | General Fund | 39760 | 39760 |  | 17040 | 17040 |  | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-04 | n/a | 2021-03-12
| Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-04 | n/a | 2021-03-09 | 7 CD | 2021-03-09 | General Fund |  |  |  | 2444 | 2444 |  | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-04 | n/a | 2021-03-09
| Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-04 | n/a | 2021-03-09 | 7 CD | 2021-03-16 | General Fund |  |  |  | 15600 | 15600 |  | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-04 | n/a | 2021-03-16
B045012821 | Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-02 | 7 CD | 2021-03-09 | General Fund | 22500 | 22500 |  | 19400 | 19400 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-09
B046012921 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 7 CD | 2021-03-09 | General Fund | 37480 | 37480 |  | 18064 | 18064 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-09
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 7 CD | 2021-03-10 | General Fund |  |  |  | 18064 | 18064 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-10
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 7 CD | 2021-03-05 | General Fund |  |  |  | 418.44 | 418.44 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-02 | 7 CD | 2021-03-12 | General Fund |  |  |  | 2067 | 2067 |  | n/a | n/a | n/a | n/a | 2021-02-24 | n/a | n/a | 2021-03-02 | n/a | 2021-03-12
B047013021 | Vehicle and Maintenance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-18 | n/a | 2021-02-18 | 1 CD | 2021-02-24 | General Fund | 1520 | 1520 |  | 1520 | 1520 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-18 | n/a | 2021-02-24
B048013121 | Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 7 CD | 2021-05-14 | General Fund | 32200 | 32200 |  | 19885 | 19885 |  | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-02 | n/a | 2021-05-14
| Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-02 | n/a | 2021-03-05 | 60 CD | 2021-03-26 | General Fund |  |  |  | 5825 | 5825 |  | n/a | n/a | n/a | n/a | 2021-02-26 | n/a | n/a | 2021-03-02 | n/a | 2021-03-26
B049013221 | Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-02 | n/a | n/a | 2021-03-08 | n/a | 2021-03-12 | 7 CD | 2021-03-15 | General Fund | 43445 | 43445 |  | 5850 | 5850 |  | n/a | n/a | n/a | n/a | 2021-03-02 | n/a | n/a | 2021-03-08 | n/a | 2021-03-15
| Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-02 | n/a | n/a | 2021-04-12 | n/a | 2021-03-12 | 7 CD | 2021-04-27 | General Fund |  |  |  | 3300 | 3300 |  | n/a | n/a | n/a | n/a | 2021-03-02 | n/a | n/a | 2021-04-12 | n/a | 2021-04-27
| Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-02 | n/a | n/a | 2021-03-08 | n/a | 2021-03-15 | 7 CD | 2021-03-18 | General Fund |  |  |  | 4680 | 4680 |  | n/a | n/a | n/a | n/a | 2021-03-02 | n/a | n/a | 2021-03-08 | n/a | 2021-03-18
| Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-02 | n/a | n/a | 2021-03-08 | n/a | 2021-03-12 | 7 CD | 2021-03-22 | General Fund |  |  |  | 1370.25 | 1370.25 |  | n/a | n/a | n/a | n/a | 2021-03-02 | n/a | n/a | 2021-03-08 | n/a | 2021-03-22
| Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-02 | n/a | n/a | 2021-03-08 | n/a | 2021-03-08 | 7 CD | 2021-03-25 | General Fund |  |  |  | 8750 | 8750 |  | n/a | n/a | n/a | n/a | 2021-03-02 | n/a | n/a | 2021-03-08 | n/a | 2021-03-25
B050013321 | Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-03-09 | n/a | 2021-03-12 | 7 CD | 2021-03-26 | General Fund | 52000 | 52000 |  | 40050 | 40050 |  | n/a | n/a | n/a | n/a | 2021-03-04 | n/a | n/a | 2021-03-09 | n/a | 2021-03-26
B052013521 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-03-12 | 7 CD | 2021-03-15 | General Fund | 49100 | 49100 |  | 17666 | 17666 |  | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-03-15
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-03-12 | 7 CD | 2021-03-15 | General Fund |  |  |  | 17666 | 17666 |  | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-03-15
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-03-22 | 7 CD | 2021-03-23 | General Fund |  |  |  | 9998 | 9998 |  | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-03-23
B053013621 | Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-03-12 | 7 CD | 2021-03-15 | General Fund | 30000 | 30000 |  | 12900 | 12900 |  | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-03-15
| Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-03-15 | 7 CD | 2021-03-22 | General Fund |  |  |  | 5190 | 5190 |  | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-03-22
B054013721 | Kawayan Turno Pipeline | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-09 | n/a | n/a | 2021-02-04 | n/a | 2021-02-08 | 30 CD | 2021-03-08 | General Fund | 103000 | 103000 |  | 12720 | 12720 |  | n/a | n/a | n/a | n/a | 2021-03-09 | n/a | n/a | 2021-02-04 | n/a | 2021-03-08
| Kawayan Turno Pipeline | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-09 | n/a | n/a | 2021-02-04 | n/a | 2021-02-23 | 7 CD | 2021-03-12 | General Fund |  |  |  | 26048.75 | 26048.75 |  | n/a | n/a | n/a | n/a | 2021-03-09 | n/a | n/a | 2021-02-04 | n/a | 2021-03-12
| Kawayan Turno Pipeline | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-09 | n/a | n/a | 2021-03-18 | n/a | 2021-03-19 | 30 CD | 2021-03-26 | General Fund |  |  |  | 26868 | 26868 |  | n/a | n/a | n/a | n/a | 2021-03-09 | n/a | n/a | 2021-03-18 | n/a | 2021-03-26
B055013821 | Vehicle and Maintenance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-24 | n/a | 2021-02-24 | 1 CD | 2021-03-05 | General Fund | 2500 | 2500 |  | 2500 | 2500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-24 | n/a | 2021-03-05
B056013921 | Vehicle and Maintenance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-24 | n/a | 2021-02-24 | 1 CD | 2021-03-05 | General Fund | 1041.5 | 1041.5 |  | 1041.5 | 1041.5 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-24 | n/a | 2021-03-05
B057014021 | Office Building Maintenance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-24 | n/a | 2021-02-24 | 7 CD | 2021-03-05 | General Fund | 13500 | 13500 |  | 13500 | 13500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-02-24 | n/a | 2021-03-05
B059014221 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-03-15 | 7 CD | 2021-04-08 | General Fund | 15000 | 15000 |  | 14500 | 14500 |  | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-09 | n/a | 2021-04-08
B060014321 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-08 | n/a | 2021-03-10 | 7 CD | 2021-04-13 | General Fund | 49500 | 49500 |  | 42509.5 | 42509.5 |  | n/a | n/a | n/a | n/a | 2021-03-03 | n/a | n/a | 2021-03-08 | n/a | 2021-04-13
B061014421 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-23 | 7 CD | 2021-03-29 | General Fund | 16550 | 16550 |  | 5400 | 5400 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-29
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-23 | 7 CD | 2021-04-05 | General Fund |  |  |  | 6240 | 6240 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-04-05
B062014521 | Engineering | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-11 | n/a | n/a | 2021-03-18 | n/a | 2021-03-18 | 7 CD | 2021-04-06 | General Fund | 10000 | 10000 |  | 4995 | 4995 |  | n/a | n/a | n/a | n/a | 2021-03-11 | n/a | n/a | 2021-03-18 | n/a | 2021-04-06
B064014721 | Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-03-25 | n/a | 2021-03-29 | 7 CD | 2021-04-08 | General Fund | 194000 | 194000 |  | 74000 | 74000 |  | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-03-25 | n/a | 2021-04-08
| Vehicle and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-03-25 | n/a | 2021-03-30 | 7 CD | 2021-04-08 | General Fund |  |  |  | 75838 | 75838 |  | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-03-25 | n/a | 2021-04-08
B065014821 | Pumping Station | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-05 | n/a | 2021-03-05 | 7 CD | 2021-03-18 | General Fund | 6500 | 6500 |  | 6500 | 6500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-05 | n/a | 2021-03-18
B066014921 | Vehicle and Maintenance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-09 | n/a | 2021-03-09 | 1 CD | 2021-03-18 | General Fund | 1440 | 1440 |  | 1440 | 1440 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-09 | n/a | 2021-03-18
B067015021 | Vehicle and Maintenance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-10 | n/a | 2021-03-10 | 1 CD | 2021-03-15 | General Fund | 3517.38 | 3517.38 |  | 3517.36 | 3517.36 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-10 | n/a | 2021-03-15
B068015121 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-03-25 | n/a | 2021-03-25 | 7 CD | 2021-03-26 | General Fund | 106450 | 106450 |  | 35 | 35 |  | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-03-25 | n/a | 2021-03-26
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-04-07 | n/a | 2021-04-13 | 7 CD | 2021-04-13 | General Fund |  |  |  | 1920 | 1920 |  | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-04-07 | n/a | 2021-04-13
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-03-25 | n/a | 2021-03-26 | 7 CD | 2021-03-30 | General Fund |  |  |  | 30480 | 30480 |  | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-03-25 | n/a | 2021-03-30
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-04-07 | n/a | 2021-04-14 | 7 CD | 2021-04-26 | General Fund |  |  |  | 10800 | 10800 |  | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-04-07 | n/a | 2021-04-26
B069015221 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-11 | n/a | n/a | 2021-03-16 | n/a | 2021-03-19 | 7 CD | 2021-03-29 | General Fund | 2250 | 2250 |  | 1400 | 1400 |  | n/a | n/a | n/a | n/a | 2021-03-11 | n/a | n/a | 2021-03-16 | n/a | 2021-03-29
B073016521 | Vehicle and Maintenance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-09 | n/a | 2021-03-09 | 1 CD | 2021-04-13 | General Fund | 18500 | 18500 |  | 18500 | 18500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-09 | n/a | 2021-04-13
B074016621 | Vehicle and Maintenance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-09 | n/a | 2021-03-09 | 1 CD | 2021-03-18 | General Fund | 950 | 950 |  | 950 | 950 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-09 | n/a | 2021-03-18
B076016821 | Vehicle and Maintenance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-09 | n/a | 2021-03-09 | 1 CD | 2021-03-18 | General Fund | 3520 | 3520 |  | 3520 | 3520 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-09 | n/a | 2021-03-18
C001015321 | Office Building Maintenance | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-09 | n/a | n/a | 2021-03-16 | n/a | 2021-03-19 | 7 CD | 2021-03-19 | General Fund | 900 | 900 |  | 894 | 894 |  | n/a | n/a | n/a | n/a | 2021-03-09 | n/a | n/a | 2021-03-16 | n/a | 2021-03-19
C002015421 | Well 8 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-23 | 7 CD | 2021-03-24 | General Fund | 12750 | 12750 |  | 1410 | 1410 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-24
| Well 8 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-19 | 7 CD | 2021-03-30 | General Fund |  |  |  | 6000 | 6000 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-19 | n/a | 2021-03-30
C003015521 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-03-25 | n/a | 2021-03-24 | 30 CD | 2021-05-18 | General Fund | 990000 | 990000 |  | 967500 | 967500 |  | n/a | n/a | n/a | n/a | 2021-03-23 | n/a | n/a | 2021-03-25 | n/a | 2021-05-18
C004015621 | Well 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-11 | n/a | n/a | 2021-03-19 | n/a | 2021-03-25 | 7 CD | 2021-03-29 | General Fund | 30178 | 30178 |  | 7711 | 7711 |  | n/a | n/a | n/a | n/a | 2021-03-11 | n/a | n/a | 2021-03-19 | n/a | 2021-03-29
| Well 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-11 | n/a | n/a | 2021-03-19 | n/a | 2021-03-23 | 7 CD | 2021-03-30 | General Fund |  |  |  | 700 | 700 |  | n/a | n/a | n/a | n/a | 2021-03-11 | n/a | n/a | 2021-03-19 | n/a | 2021-03-30
C005015721 | Commercial | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-17 | n/a | 2021-03-19 | 7 CD | 2021-03-26 | General Fund | 400000 | 400000 |  | 280000 | 280000 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-17 | n/a | 2021-03-26
C006015821 | Repair and Maintenance | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-05-19 | 45 CD | 2021-06-08 | General Fund | 23750 | 23750 |  | 21890 | 21890 |  | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-06-08
C009016121 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-09 | n/a | 2021-03-09 | 1 CD | 2021-03-18 | General Fund | 16800 | 16800 |  | 16800 | 16800 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-09 | n/a | 2021-03-18
C010016921 | Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-18 | n/a | 2021-03-19 | 7 CD | 2021-03-19 | General Fund | 3600 | 3600 |  | 1200 | 1200 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-18 | n/a | 2021-03-19
C012017121 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-18 | n/a | 2021-03-19 | 7 CD | 2021-03-19 | General Fund | 10150 | 10150 |  | 6081 | 6081 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-03-18 | n/a | 2021-03-19
C013017221 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-26 | n/a | 2021-03-26 | 1 CD | 2021-04-05 | General Fund | 10900 | 10900 |  | 10900 | 10900 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-26 | n/a | 2021-04-05
C015017421 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-05 | n/a | n/a | 2021-03-10 | n/a | 2021-03-10 | 7 CD | 2021-03-12 | General Fund | 6260 | 6260 |  | 4667 | 4667 |  | n/a | n/a | n/a | n/a | 2021-03-05 | n/a | n/a | 2021-03-10 | n/a | 2021-03-12
C016017521 | Office | Admin | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-18 | n/a | n/a | 2021-03-26 | n/a | 2021-03-26 | 30 CD | 2021-06-09 | General Fund | 350000 | 350000 |  | 250000 | 250000 |  | n/a | n/a | n/a | n/a | 2021-03-18 | n/a | n/a | 2021-03-26 | n/a | 2021-06-09
| Office | Admin | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-18 | n/a | n/a | 2021-03-26 | n/a | 2021-03-26 | 30 CD | 2021-06-28 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-03-18 | n/a | n/a | 2021-03-26 | n/a | 2021-06-28
C019017821 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-04-07 | 7 CD | 2021-04-23 | General Fund | 8000 | 8000 |  | 1800 | 1800 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-04-23
C023018221 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-04-16 | n/a | 2021-04-19 | 7 CD | 2021-04-21 | General Fund | 900 | 900 |  | 895 | 895 |  | n/a | n/a | n/a | n/a | 2021-03-16 | n/a | n/a | 2021-04-16 | n/a | 2021-04-21
C024018321 | WELL 19 | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-23 | n/a | 2021-03-23 | 1 CD | 2021-03-23 | General Fund | 23000 | 23000 |  | 23000 | 23000 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-23 | n/a | 2021-03-23
C025018421 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-23 | n/a | 2021-03-23 | 1 CD | 2021-03-30 | General Fund | 5640 | 5640 |  | 640 | 640 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-23 | n/a | 2021-03-30
C026018521 | Commercial | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-09 | n/a | n/a | 2021-03-22 | n/a | 2021-03-23 | 7 CD | 2021-03-23 | General Fund | 4500 | 4500 |  | 4000 | 4000 |  | n/a | n/a | n/a | n/a | 2021-03-09 | n/a | n/a | 2021-03-22 | n/a | 2021-03-23
C028018721 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-04-12 | n/a | 2021-04-15 | 7 CD | 2021-04-16 | General Fund | 11000 | 11000 |  | 3710 | 3710 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-04-12 | n/a | 2021-04-16
C029018821 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-03-30 | 7 CD | 2021-04-19 | General Fund | 15000 | 15000 |  | 9912 | 9912 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-04-19
C031019021 | Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-20 | n/a | 2021-04-21 | 7 CD | 2021-04-21 | General Fund | 30830 | 30830 |  | 4920 | 4920 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-20 | n/a | 2021-04-21
| Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-20 | n/a | 2021-04-21 | 7 CD | 2021-04-22 | General Fund |  |  |  | 2370 | 2370 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-20 | n/a | 2021-04-22
C032019121 | Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-12 | n/a | 2021-04-15 | 7 CD | 2021-04-15 | General Fund | 1600 | 1600 |  | 2800 | 2800 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-12 | n/a | 2021-04-15
C033019221 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-08 | n/a | n/a | 2021-04-14 | n/a | 2021-04-16 | 45 CD | 2021-05-19 | General Fund | 949700 | 949700 |  | 140550 | 140550 |  | n/a | n/a | n/a | n/a | 2021-04-08 | n/a | n/a | 2021-04-14 | n/a | 2021-05-19
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-08 | n/a | n/a | 2021-04-14 | n/a | 2021-04-16 | 45 CD | 2021-05-27 | General Fund |  |  |  | 745964 | 745964 |  | n/a | n/a | n/a | n/a | 2021-04-08 | n/a | n/a | 2021-04-14 | n/a | 2021-05-27
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-08 | n/a | n/a | 2021-04-14 | n/a | 2021-04-16 | 45 CD | 2021-06-08 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-04-08 | n/a | n/a | 2021-04-14 | n/a | 2021-06-08
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-08 | n/a | n/a | 2021-04-14 | n/a | 2021-04-16 | 45 CD | 2021-05-11 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-04-08 | n/a | n/a | 2021-04-14 | n/a | 2021-05-11
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-08 | n/a | n/a | 2021-04-14 | n/a | 2021-04-16 | 45 CD | 2021-06-25 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-04-08 | n/a | n/a | 2021-04-14 | n/a | 2021-06-25
C034019321 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-19 | n/a | 2021-03-19 | 1 CD | 2021-03-26 | General Fund | 3260 | 3260 |  | 1300 | 1300 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-19 | n/a | 2021-03-26
| Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-19 | n/a | 2021-03-19 | 1 CD | 2021-03-26 | General Fund |  |  |  | 1960 | 1960 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-19 | n/a | 2021-03-26
C035019421 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-16 | n/a | 2021-04-19 | 7 CD | 2021-04-20 | General Fund | 77500 | 77500 |  | 74400 | 74400 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-16 | n/a | 2021-04-20
C036019521 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-05-25 | 7 CD | 2021-05-28 | General Fund | 23940 | 23940 |  | 16990 | 16990 |  | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-05-28
| Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-05-25 | 7 CD | 2021-06-04 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-06-04
| Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-05-25 | 7 CD | 2021-06-22 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-06-22
C037019621 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-19 | n/a | 2021-03-19 | 1 CD | 2021-04-13 | General Fund | 5130 | 5130 |  | 5130 | 5130 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-19 | n/a | 2021-04-13
C038019721 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-19 | n/a | 2021-03-19 | 7 CD | 2021-03-26 | General Fund | 12100 | 12100 |  | 12100 | 12100 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-19 | n/a | 2021-03-26
C039019821 | Engineering Office | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-06-10 | n/a | n/a | 2021-06-11 | n/a | 2021-06-16 | 7 CD | 2021-06-23 | General Fund | 80000 | 80000 |  | 33800 | 33800 |  | n/a | n/a | n/a | n/a | 2021-06-10 | n/a | n/a | 2021-06-11 | n/a | 2021-06-23
| Engineering Office | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-06-10 | n/a | n/a | 2021-06-11 | n/a | 2021-06-14 | 7 CD | 2021-06-21 | General Fund |  |  |  | 11995 | 11995 |  | n/a | n/a | n/a | n/a | 2021-06-10 | n/a | n/a | 2021-06-11 | n/a | 2021-06-21
C040019921 | Well 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-04-07 | 7 CD | 2021-04-07 | General Fund | 11075 | 11075 |  | 2202 | 2202 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-04-07
| Well 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-04-06 | 7 CD | 2021-04-12 | General Fund |  |  |  | 2268 | 2268 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-04-12
| Well 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-04-07 | 7 CD | 2021-04-14 | General Fund |  |  |  | 3125 | 3125 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-04-14
C041020021 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-04-07 | 7 CD | 2021-04-07 | General Fund | 3500 | 3500 |  | 900 | 900 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-30 | n/a | 2021-04-07
C042020121 | Booster Pump | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-26 | n/a | 2021-04-05 | 7 CD | 2021-04-07 | General Fund | 3000 | 3000 |  | 3000 | 3000 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-26 | n/a | 2021-04-07
C043020221 | well 8 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-26 | n/a | 2021-04-05 | 7 CD | 2021-04-16 | General Fund | 4620 | 4620 |  | 4620 | 4620 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-26 | n/a | 2021-04-16
C044020321 | Pumping Station | IT | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-26 | n/a | 2021-03-26 | 7 CD | 2021-03-30 | General Fund | 250 | 250 |  | 250 | 250 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-26 | n/a | 2021-03-30
C045020421 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-25 | n/a | 2021-03-25 | 7 CD | 2021-04-05 | General Fund | 1620 | 1620 |  | 1620 | 1620 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-25 | n/a | 2021-04-05
C047020621 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-30 | n/a | n/a | 2021-04-12 | n/a | 2021-04-16 | 7 CD | 2021-04-19 | General Fund | 32018 | 32018 |  | 12324.85 | 12324.85 |  | n/a | n/a | n/a | n/a | 2021-03-30 | n/a | n/a | 2021-04-12 | n/a | 2021-04-19
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-30 | n/a | n/a | 2021-04-12 | n/a | 2021-04-16 | 7 CD | 2021-04-19 | General Fund |  |  |  | 3792 | 3792 |  | n/a | n/a | n/a | n/a | 2021-03-30 | n/a | n/a | 2021-04-12 | n/a | 2021-04-19
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-30 | n/a | n/a | 2021-04-12 | n/a | 2021-04-16 | 7 CD | 2021-04-20 | General Fund |  |  |  | 10656 | 10656 |  | n/a | n/a | n/a | n/a | 2021-03-30 | n/a | n/a | 2021-04-12 | n/a | 2021-04-20
C048020721 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-27 | n/a | 2021-05-18 | 7 CD | 2021-05-24 | General Fund | 32000 | 32000 |  | 31780 | 31780 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-27 | n/a | 2021-05-24
C049020821 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-15 | n/a | 2021-04-20 | 7 CD | 2021-04-21 | General Fund | 24000 | 24000 |  | 625 | 625 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-15 | n/a | 2021-04-21
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-15 | n/a | 2021-04-19 | 7 CD | 2021-04-22 | General Fund |  |  |  | 2915 | 2915 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-15 | n/a | 2021-04-22
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-15 | n/a | 2021-04-19 | 7 CD | 2021-04-26 | General Fund |  |  |  | 1320 | 1320 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-15 | n/a | 2021-04-26
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-15 | n/a | 2021-04-19 | 7 CD | 2021-04-26 | General Fund |  |  |  | 460 | 460 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-15 | n/a | 2021-04-26
C050020921 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-26 | n/a | 2021-04-29 | 7 CD | 2021-06-14 | General Fund | 50000 | 50000 |  | 42950 | 42950 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-26 | n/a | 2021-06-14
C052021121 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-13 | n/a | 2021-04-16 | 7 CD | 2021-04-16 | General Fund | 1500 | 1500 |  | 1450 | 1450 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-13 | n/a | 2021-04-16
C053021221 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-14 | n/a | 2021-04-14 | 30 CD | 2021-05-31 | General Fund | 173900 | 173900 |  | 143000 | 143000 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-14 | n/a | 2021-05-31
C054021321 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-15 | n/a | 2021-05-01 | 30 CD | 2021-05-10 | General Fund | 150000 | 150000 |  | 131648 | 131648 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-15 | n/a | 2021-05-10
C055021421 | Pumping Station | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-16 | 1 CD | 2021-04-15 | General Fund | 93375 | 93375 |  | 93375 | 93375 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-15
C057021621 | Commercial | Admin | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-12 | n/a | 2021-04-13 | 7 CD | 2021-04-13 | General Fund | 9600 | 9600 |  | 8780 | 8780 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-12 | n/a | 2021-04-13
C061022021 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-12 | n/a | 2021-04-15 | 7 CD | 2021-04-15 | General Fund | 85400 | 85400 |  | 75800 | 75800 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-12 | n/a | 2021-04-15
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-22 | n/a | 2021-04-27 | 7 CD | 2021-04-27 | General Fund |  |  |  | 1160 | 1160 |  | n/a | n/a | n/a | n/a | 2021-04-06 | n/a | n/a | 2021-04-22 | n/a | 2021-04-27
C062022121 | Pumping Station | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-25 | n/a | 2021-03-25 | 1 CD | 2021-03-30 | General Fund | 150 | 150 |  | 150 | 150 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-25 | n/a | 2021-03-30
C063022221 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-25 | n/a | 2021-03-25 | 1 CD | 2021-03-30 | General Fund | 1350 | 1350 |  | 1350 | 1350 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-25 | n/a | 2021-03-30
C064022321 | Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-15 | n/a | 2021-04-19 | 45 CD | 2021-05-11 | General Fund | 63500 | 63500 |  | 49554.6 | 49554.6 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-15 | n/a | 2021-05-11
C065022421 | Pumping Station | Engineering | Public Bidding | n/a | n/a | 2021-03-29 | 2021-03-29 | 2021-04-15 | 2021-04-15 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-05-04 | 120 CD | 2021-06-03 | General Fund | 7200000 |  | 7200000 | 6012000 |  | 6012000 | COA/DCCI/JAYCEES | n/a | 2021-03-29 | 2021-03-29 | 2021-04-15 | 2021-04-15 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-06-03
C066022521 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-29 | n/a | 2021-03-29 | 1 CD | 2021-04-13 | General Fund | 150 | 150 |  | 150 | 150 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-03-29 | n/a | 2021-04-13
C069022821 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-16 | n/a | 2021-04-19 | 7 CD | 2021-04-23 | General Fund | 25000 | 25000 |  | 19125 | 19125 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-16 | n/a | 2021-04-23
C070022921 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-18 | n/a | 2021-04-19 | 7 CD | 2021-04-19 | General Fund | 22000 | 22000 |  | 3429 | 3429 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-18 | n/a | 2021-04-19
| Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-18 | n/a | 2021-04-19 | 7 CD | 2021-04-26 | General Fund |  |  |  | 6720 | 6720 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-18 | n/a | 2021-04-26
C071023021 | Well 7 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-05-20 | 7 CD | 2021-05-20 | General Fund | 407640 | 407640 |  | 86000 | 86000 |  | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-05-20
| Well 7 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-27 | n/a | 2021-06-14 | 7 CD | 2021-06-18 | General Fund |  |  |  | 283350 | 283350 |  | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-27 | n/a | 2021-06-18
| Well 7 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-05-10 | 7 CD | 2021-05-28 | General Fund |  |  |  | 26229 | 26229 |  | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-05-28
| Well 7 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-05-10 | 7 CD | 2021-06-14 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-06-14
C073023221 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-14 | n/a | 2021-04-16 | 7 CD | 2021-04-19 | General Fund | 12635 | 12635 |  | 2615.5 | 2615.5 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-14 | n/a | 2021-04-19
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-14 | n/a | 2021-04-16 | 7 CD | 2021-04-19 | General Fund |  |  |  | 967.32 | 967.32 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-14 | n/a | 2021-04-19
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-14 | n/a | 2021-04-16 | 7 CD | 2021-04-20 | General Fund |  |  |  | 6120 | 6120 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-14 | n/a | 2021-04-20
C074023321 | Office Supplies | Admin | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-14 | n/a | 2021-04-14 | 7 CD | 2021-04-16 | General Fund | 1000 | 1000 |  | 180 | 180 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-14 | n/a | 2021-04-16
C075023421 | Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-16 | n/a | 2021-04-20 | 7 CD | 2021-04-21 | General Fund | 42000 | 42000 |  | 2300 | 2300 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-16 | n/a | 2021-04-21
| Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-16 | n/a | 2021-04-20 | 7 CD | 2021-05-04 | General Fund |  |  |  | 36000 | 36000 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-16 | n/a | 2021-05-04
C076023521 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-16 | n/a | 2021-04-19 | 7 CD | 2021-04-26 | General Fund | 13500 | 13500 |  | 9900 | 9900 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-16 | n/a | 2021-04-26
C078023721 | Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-15 | n/a | 2021-04-19 | 7 CD | 2021-04-26 | General Fund | 2000 | 2000 |  | 1800 | 1800 |  | n/a | n/a | n/a | n/a | 2021-04-13 | n/a | n/a | 2021-04-15 | n/a | 2021-04-26
C079023821 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-06 | n/a | 2021-04-06 | 1 CD | 2021-04-13 | General Fund | 5600 | 5600 |  | 5600 | 5600 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-06 | n/a | 2021-04-13
C080023921 | Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-04-22 | 30 CD | 2021-05-04 | General Fund | 75000 | 75000 |  | 42600 | 42600 |  | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-05-04
| Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-04-22 | 45 CD | 2021-05-27 | General Fund |  |  |  | 12500 | 12500 |  | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-05-27
C081024021 | Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-16 | n/a | n/a | 2021-04-20 | n/a | 2021-04-20 | 7 CD | 2021-04-26 | General Fund | 65000 | 65000 |  | 54150 | 54150 |  | n/a | n/a | n/a | n/a | 2021-04-16 | n/a | n/a | 2021-04-20 | n/a | 2021-04-26
| Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-16 | n/a | n/a | 2021-04-20 | n/a | 2021-04-20 | 7 CD | 2021-05-04 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-04-16 | n/a | n/a | 2021-04-20 | n/a | 2021-05-04
C082024121 | Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-30 | n/a | n/a | 2021-05-03 | n/a | 2021-05-26 | 7 CD | 2021-05-26 | General Fund | 104500 | 104500 |  | 103750 | 103750 |  | n/a | n/a | n/a | n/a | 2021-04-30 | n/a | n/a | 2021-05-03 | n/a | 2021-05-26
| Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-30 | n/a | n/a | 2021-05-03 | n/a | 2021-05-26 | 7 CD | 2021-05-31 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-04-30 | n/a | n/a | 2021-05-03 | n/a | 2021-05-31
C086024521 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-08 | n/a | 2021-04-08 | 1 CD | 2021-04-21 | General Fund | 216374.29 | 216374.29 |  | 216374.29 | 216374.29 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-08 | n/a | 2021-04-21
C087024621 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-03-29 | n/a | 2021-04-27 | 30 CD | 2021-06-21 | General Fund | 336000 | 336000 |  | 230000 | 230000 |  | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-03-29 | n/a | 2021-06-21
C088025221 | Office Supplies | Admin | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-25 | n/a | 2021-03-26 | 7 CD | 2021-03-26 | General Fund | 42500 | 42500 |  | 29995 | 29995 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-25 | n/a | 2021-03-26
| Office Supplies | Admin | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-25 | n/a | 2021-03-25 | 7 CD | 2021-03-30 | General Fund |  |  |  | 10566.04 | 10566.04 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-25 | n/a | 2021-03-30
C089025321 | Office Supplies | Admin | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-29 | n/a | n/a | 2021-03-25 | n/a | 2021-03-29 | 7 CD | 2021-03-29 | General Fund | 45000 | 45000 |  | 43999 | 43999 |  | n/a | n/a | n/a | n/a | 2021-03-29 | n/a | n/a | 2021-03-25 | n/a | 2021-03-29
C090026721 | Office Supplies | Admin | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-29 | n/a | 2021-03-30 | 7 CD | 2021-03-30 | General Fund | 3200 | 3200 |  | 3190 | 3190 |  | n/a | n/a | n/a | n/a | 2021-03-25 | n/a | n/a | 2021-03-29 | n/a | 2021-03-30
D002024821 | Office Building Maintencance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-04-20 | n/a | 2021-04-20 | 7 CD | 2021-04-23 | General Fund | 22500 | 22500 |  | 7200 | 7200 |  | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-04-20 | n/a | 2021-04-23
D003024921 | Office Building Maintencance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-05-25 | 7 CD | 2021-06-01 | General Fund | 1500 | 1500 |  | 778 | 778 |  | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-05-12 | n/a | 2021-06-01
D004025021 | Pumping Station | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-04-16 | n/a | 2021-04-19 | 7 CD | 2021-04-19 | General Fund | 3200 | 3200 |  | 2970.7 | 2970.7 |  | n/a | n/a | n/a | n/a | 2021-04-15 | n/a | n/a | 2021-04-16 | n/a | 2021-04-19
D005025121 | Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-04-22 | 7 CD | 2021-04-27 | General Fund | 3000 | 3000 |  | 1200 | 1200 |  | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-04-27
D006025421 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-14 | 1 CD | 2021-04-21 | General Fund | 2500 | 2500 |  | 2500 | 2500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-21
D007025521 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-14 | 1 CD | 2021-04-19 | General Fund | 3160 | 3160 |  | 3160 | 3160 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-19
D009025721 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-14 | 1 CD | 2021-04-19 | General Fund | 1850 | 1850 |  | 1850 | 1850 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-19
D010025821 | Septage and Treatment Plant | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-04-27 | 7 CD | 2021-04-27 | General Fund | 14700 | 14700 |  | 14000 | 14000 |  | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-04-27
| Septage and Treatment Plant | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-04-27 | 7 CD | 2021-05-25 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-05-25
D011025921 | Office Supplies | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-05-12 | n/a | 2021-05-20 | 7 CD | 2021-05-21 | General Fund | 14500 | 14500 |  | 13850 | 13850 |  | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-05-12 | n/a | 2021-05-21
D012026021 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-14 | 1 CD | 2021-04-21 | General Fund | 130 | 130 |  | 130 | 130 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-21
D013026121 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-14 | 1 CD | 2021-04-21 | General Fund | 2800 | 2800 |  | 2800 | 2800 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-21
D014026221 | Pumping Station | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-14 | 1 CD | 2021-04-21 | General Fund | 4000 | 4000 |  | 4000 | 4000 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-14 | n/a | 2021-04-21
D015026321 | Pumping Station | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-15 | n/a | 2021-04-15 | 1 CD | 2021-04-21 | General Fund | 23000 | 23000 |  | 23000 | 23000 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-15 | n/a | 2021-04-21
D016026421 | Office Supplies | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-04-27 | 7 CD | 2021-05-04 | General Fund | 14500 | 14500 |  | 13700 | 13700 |  | n/a | n/a | n/a | n/a | 2021-04-20 | n/a | n/a | 2021-04-22 | n/a | 2021-05-04
D017026521 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-16 | n/a | n/a | 2021-04-20 | n/a | 2021-04-27 | 7 CD | 2021-04-27 | General Fund | 40755 | 40755 |  | 36132.3 | 36132.3 |  | n/a | n/a | n/a | n/a | 2021-04-16 | n/a | n/a | 2021-04-20 | n/a | 2021-04-27
D018026621 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-15 | n/a | 2021-04-15 | 7 CD | 2021-04-21 | General Fund | 2200 | 2200 |  | 2200 | 2200 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-15 | n/a | 2021-04-21
D019026821 | Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-30 | n/a | n/a | 2021-05-04 | n/a | 2021-05-04 | 7 CD | 2021-06-03 | General Fund | 999960 | 999960 |  | 840351 | 840351 |  | n/a | n/a | n/a | n/a | 2021-04-30 | n/a | n/a | 2021-05-04 | n/a | 2021-06-03
| Vehicle and Heavy Equipment | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-30 | n/a | n/a | 2021-05-04 | n/a | 2021-05-04 | 7 CD | 2021-06-22 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-04-30 | n/a | n/a | 2021-05-04 | n/a | 2021-06-22
D020026921 | Office Supplies | Admin | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-23 | n/a | n/a | 2021-05-04 | n/a | 2021-05-04 | 7 CD | 2021-05-17 | General Fund | 2000 | 2000 |  | 1598 | 1598 |  | n/a | n/a | n/a | n/a | 2021-04-23 | n/a | n/a | 2021-05-04 | n/a | 2021-05-17
D021027021 | IT | IT | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-28 | n/a | n/a | 2021-05-31 | n/a | 2021-06-09 | 15 CD | 2021-06-14 | General Fund | 494000 | 494000 |  | 344000 | 344000 |  | n/a | n/a | n/a | n/a | 2021-05-28 | n/a | n/a | 2021-05-31 | n/a | 2021-06-14
| IT | IT | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-28 | n/a | n/a | 2021-05-31 | n/a | 2021-06-09 | 15 CD | 2021-06-23 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-05-28 | n/a | n/a | 2021-05-31 | n/a | 2021-06-23
| IT | IT | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-28 | n/a | n/a | 2021-05-31 | n/a | 2021-06-08 | 15 CD | 2021-06-21 | General Fund |  |  |  | 98000 | 98000 |  | n/a | n/a | n/a | n/a | 2021-05-28 | n/a | n/a | 2021-05-31 | n/a | 2021-06-21
D023027221 | Office Supplies | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-21 | n/a | n/a | 2021-04-21 | n/a | 2021-04-21 | 7 CD | 2021-04-21 | General Fund | 7500 | 7500 |  | 7340 | 7340 |  | n/a | n/a | n/a | n/a | 2021-04-21 | n/a | n/a | 2021-04-21 | n/a | 2021-04-21
D024027321 | Office Building Maintencance | Procurement | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-22 | n/a | 2021-04-22 | 1 CD | 2021-04-26 | General Fund | 7500 | 7500 |  | 7500 | 7500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-22 | n/a | 2021-04-26
D025027421 | Office Building Maintencance | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-21 | n/a | 2021-04-21 | 1 CD | 2021-04-21 | General Fund | 4150 | 4150 |  | 4150 | 4150 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-21 | n/a | 2021-04-21
D026027521 | Office Supplies | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-27 | n/a | n/a | 2021-05-12 | n/a | 2021-05-25 | 7 CD | 2021-05-25 | General Fund | 14800 | 14800 |  | 11800 | 11800 |  | n/a | n/a | n/a | n/a | 2021-04-27 | n/a | n/a | 2021-05-12 | n/a | 2021-05-25
D027027621 | Office Supplies | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-27 | n/a | n/a | 2021-05-17 | n/a | 2021-05-17 | 7 CD | 2021-05-25 | General Fund | 12000 | 12000 |  | 4250 | 4250 |  | n/a | n/a | n/a | n/a | 2021-04-27 | n/a | n/a | 2021-05-17 | n/a | 2021-05-25
| Office Supplies | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-27 | n/a | n/a | 2021-05-17 | n/a | 2021-05-25 | 7 CD | 2021-06-01 | General Fund |  |  |  | 5556 | 5556 |  | n/a | n/a | n/a | n/a | 2021-04-27 | n/a | n/a | 2021-05-17 | n/a | 2021-06-01
D028027721 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-26 | n/a | 2021-04-26 | 1 CD | 2021-04-27 | General Fund | 1400 | 1400 |  | 1400 | 1400 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-04-26 | n/a | 2021-04-27
D029027821 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-07 | n/a | 2021-05-07 | 1 CD | 2021-05-07 | General Fund | 17900 | 17900 |  | 17900 | 17900 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-07 | n/a | 2021-05-07
D030027921 | Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-04-30 | n/a | n/a | 2021-05-12 | n/a | 2021-05-17 | 7 CD | 2021-05-24 | General Fund | 30000 | 30000 |  | 27840 | 27840 |  | n/a | n/a | n/a | n/a | 2021-04-30 | n/a | n/a | 2021-05-12 | n/a | 2021-05-24
D031028021 | Vehicle and Heavy Equipment | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-19 | n/a | 2021-05-19 | 1 CD | 2021-05-19 | General Fund | 5378.83 | 5378.83 |  | 5378.83 | 5378.83 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-19 | n/a | 2021-05-19
D032028121 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-27 | n/a | n/a | 2021-05-31 | n/a | 2021-05-31 | 60 CD | 2021-06-08 | General Fund | 496250 | 496250 |  | 489939.5 | 489939.5 |  | n/a | n/a | n/a | n/a | 2021-05-27 | n/a | n/a | 2021-05-31 | n/a | 2021-06-08
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-27 | n/a | n/a | 2021-05-31 | n/a | 2021-05-31 | 60 CD | 2021-06-25 | General Fund | [6 empty] | n/a | n/a | n/a | n/a | 2021-05-27 | n/a | n/a | 2021-05-31 | n/a | 2021-06-25
D033028221 | Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-21 | n/a | n/a | 2021-05-25 | n/a | 2021-05-31 | 7 CD | 2021-05-31 | General Fund | 31840 | 31840 |  | 2820 | 2820 |  | n/a | n/a | n/a | n/a | 2021-05-21 | n/a | n/a | 2021-05-25 | n/a | 2021-05-31
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-21 | n/a | n/a | 2021-05-25 | n/a | 2021-05-31 | 7 CD | 2021-06-07 | General Fund |  |  |  | 19866.8 | 19866.8 |  | n/a | n/a | n/a | n/a | 2021-05-21 | n/a | n/a | 2021-05-25 | n/a | 2021-06-07
| Office Supplies | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-21 | n/a | n/a | 2021-05-25 | n/a | 2021-05-31 | 7 CD | 2021-05-31 | General Fund |  |  |  | 5580 | 5580 |  | n/a | n/a | n/a | n/a | 2021-05-21 | n/a | n/a | 2021-05-25 | n/a | 2021-05-31
E001028321 | Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-19 | n/a | n/a | 2021-05-24 | n/a | 2021-05-27 | 7 CD | 2021-05-27 | General Fund | 48500 | 48500 |  | 45000 | 45000 |  | n/a | n/a | n/a | n/a | 2021-05-19 | n/a | n/a | 2021-05-24 | n/a | 2021-05-27
E002028421 | Office Supplies | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-19 | n/a | n/a | 2021-05-24 | n/a | 2021-05-26 | 7 CD | 2021-05-26 | General Fund | 14000 | 14000 |  | 12980 | 12980 |  | n/a | n/a | n/a | n/a | 2021-05-19 | n/a | n/a | 2021-05-24 | n/a | 2021-05-26
E003028521 | Office Building Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-26 | n/a | n/a | 2021-05-28 | n/a | 2021-06-02 | 7 CD | 2021-06-02 | General Fund | 8500 | 8500 |  | 3500 | 3500 |  | n/a | n/a | n/a | n/a | 2021-05-26 | n/a | n/a | 2021-05-28 | n/a | 2021-06-02
E004028621 | Office Supplies | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-18 | n/a | 2021-05-18 | 1 CD | 2021-05-18 | General Fund | 100000 | 100000 |  | 77250 | 77250 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-18 | n/a | 2021-05-18
E005028721 | Office Supplies | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-05-27 | n/a | n/a | 2021-05-31 | n/a | 2021-05-31 | 15 CD | 2021-05-31 | General Fund | 49950 | 49950 |  | 49000 | 49000 |  | n/a | n/a | n/a | n/a | 2021-05-27 | n/a | n/a | 2021-05-31 | n/a | 2021-05-31
E006028821 | Office Supplies | Admin | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-06-01 | n/a | n/a | 2021-06-04 | n/a | 2021-06-07 | 7 CD | 2021-06-14 | General Fund | 14800 | 14800 |  | 14500 | 14500 |  | n/a | n/a | n/a | n/a | 2021-06-01 | n/a | n/a | 2021-06-04 | n/a | 2021-06-14
E007028921 | Office Supplies | Procurement | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-27 | n/a | 2021-05-27 | 1 CD | 2021-05-26 | General Fund | 19000 | 19000 |  | 17500 | 17500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-27 | n/a | 2021-05-26
E008029021 | Pumping Station | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-06-04 | n/a | 2021-06-04 | 1 CD | 2021-06-04 | General Fund | 5500 | 5500 |  | 5500 | 5500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-06-04 | n/a | 2021-06-04
E014029621 | Office Building Maintenance | Procurement | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-06-04 | n/a | 2021-06-04 | 1 CD | 2021-06-14 | General Fund | 22500 | 22500 |  | 22500 | 22500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-06-04 | n/a | 2021-06-14
E020030221 | Vehicle and Heavy Equipt | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-31 | n/a | 2021-05-31 | 1 CD | 2021-05-31 | General Fund | 3500 | 3500 |  | 3500 | 3500 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-31 | n/a | 2021-05-31
E021030321 | Vehicle and Heavy Equipt | Engineering | Emergency | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-28 | n/a | 2021-05-28 | 1 CD | 2021-05-28 | General Fund | 3050 | 3050 |  | 3050 | 3050 |  | n/a | n/a | n/a | n/a |  | n/a | n/a | 2021-05-28 | n/a | 2021-05-28
F002030521 | Commercial | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-06-15 | n/a | n/a | 2021-06-16 | n/a | 2021-06-18 | 7 CD | 2021-06-22 | General Fund | 49000 | 49000 |  | 41160 | 41160 |  | n/a | n/a | n/a | n/a | 2021-06-15 | n/a | n/a | 2021-06-16 | n/a | 2021-06-22
F005030821 | Repair and Maintenance | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-06-22 | n/a | n/a | 2021-06-25 | n/a | 2021-06-30 | 45 CD | 2021-07-19 | General Fund | 230000 | 230000 |  | 142690 | 142690 |  | n/a | n/a | n/a | n/a | 2021-06-22 | n/a | n/a | 2021-06-25 | n/a | 2021-07-19
F011031821 | Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-06-22 | n/a | n/a | 2021-06-23 | n/a | 2021-06-25 | 7 CD | 2021-06-25 | General Fund | 15000 | 15000 |  | 13850 | 13850 |  | n/a | n/a | n/a | n/a | 2021-06-22 | n/a | n/a | 2021-06-23 | n/a | 2021-06-25
F012031921 | Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-06-24 | n/a | n/a | 2021-06-25 | n/a | 2021-06-28 | 7 CD | 2021-06-28 | General Fund | 22800 | 22800 |  | 20700 | 20700 |  | n/a | n/a | n/a | n/a | 2021-06-24 | n/a | n/a | 2021-06-25 | n/a | 2021-06-28
F018032721 | Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-07-13 | n/a | n/a | 2021-07-19 | n/a | 2021-07-21 | 7 CD | 2021-07-21 | General Fund | 950 | 950 |  | 820 | 820 |  | n/a | n/a | n/a | n/a | 2021-07-13 | n/a | n/a | 2021-07-19 | n/a | 2021-07-21
F022033121 | Commercial | Commercial | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-06-30 | n/a | n/a | 2021-07-13 | n/a | 2021-07-22 | 7 CD | 2021-07-22 | General Fund | 10000 | 10000 |  | 7000 | 7000 |  | n/a | n/a | n/a | n/a | 2021-06-30 | n/a | n/a | 2021-07-13 | n/a | 2021-07-22
F025033421 | Well 15 | Engineering | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-07-06 | n/a | n/a | 2021-07-12 | n/a | 2021-07-15 | 7 CD | 2021-07-16 | General Fund | 10000 | 10000 |  | 8400 | 8400 |  | n/a | n/a | n/a | n/a | 2021-07-06 | n/a | n/a | 2021-07-12 | n/a | 2021-07-16
F030033921 | Office Supply | Procurement | Small Value Proc. | n/a | n/a | n/a | n/a | 2021-07-01 | n/a | n/a | 2021-07-06 | n/a | 2021-07-08 | 7 CD | 2021-07-08 | General Fund | 10140 | 10140 |  | 8580 | 8580 |  | n/a | n/a | n/a | n/a | 2021-07-01 | n/a | n/a | 2021-07-06 | n/a | 2021-07-08
F033034221 | Office Supply | Procurement | Shopping | n/a | n/a | n/a | n/a | 2021-07-09 | n/a | n/a | 2021-07-13 | n/a | 2021-07-15 | 7 CD | 2021-07-15 | General Fund | 46600 | 46600 |  | 15200 | 15200 |  | n/a | n/a | n/a | n/a | 2021-07-09 | n/a | n/a | 2021-07-13 | n/a | 2021-07-15
| Office Supply | Procurement | Shopping | n/a | n/a | n/a | n/a | 2021-07-09 | n/a | n/a | 2021-07-13 | n/a | 2021-07-15 | 7 CD | 2021-07-15 | General Fund |  |  |  | 3120 | 3120 |  | n/a | n/a | n/a | n/a | 2021-07-09 | n/a | n/a | 2021-07-13 | n/a | 2021-07-15
| Office Supply | Procurement | Shopping | n/a | n/a | n/a | n/a | 2021-07-09 | n/a | n/a | 2021-07-13 | n/a | 2021-07-15 | 7 CD | 2021-07-15 | General Fund |  |  |  | 7650 | 7650 |  | n/a | n/a | n/a | n/a | 2021-07-09 | n/a | n/a | 2021-07-13 | n/a | 2021-07-15
| Office Supply | Procurement | Shopping | n/a | n/a | n/a | n/a | 2021-07-09 | n/a | n/a | 2021-07-13 | n/a | 2021-07-15 | 7 CD | 2021-07-19 | General Fund |  |  |  | 7200 | 7200 |  | n/a | n/a | n/a | n/a | 2021-07-09 | n/a | n/a | 2021-07-13 | n/a | 2021-07-19
| Office Supply | Procurement | Shopping | n/a | n/a | n/a | n/a | 2021-07-09 | n/a | n/a | 2021-07-13 | n/a | 2021-07-15 | 7 CD | 2021-07-15 | General Fund |  |  |  | 1300.5 | 1300.5 |  | n/a | n/a | n/a | n/a | 2021-07-09 | n/a | n/a | 2021-07-13 | n/a | 2021-07-15
Total Alloted Budget of Procurement Activities | [16 empty] | 22267924.21 | 15067924.21 | 7200000 | 18900826.12 | 12888826.12 | 6012000
Total Contract Price of Procurement Actitvites Conducted
[12 empty] | Total Savings (Total Alloted Budget - Total Contract Price) |  |  |  |  | 3367098.09
|  |  | Prepared by: | [7 empty] | Recommended for Approval by: | [8 empty] | APPROVED:
|  |  | RICHARD DEAN B. DAGPIN | [7 empty] | NURSIVA S. TOME | [8 empty] | RUEL D. TABADA
|  |  | BAC Secretariat | [7 empty] | BAC Chairperson | [8 empty] | Head of the Procuring Entity
Formulas:
Sub/Open of Bids = [Sub/Open of Bids]
Notice of Award = [Notice of Award]
Delivery/ Accept = [Acceptance/ Turnover]
Pre-bid Conf = [Pre-bid Conf]
Eligibility Check = [Eligibility Check]
Bid Evaluation = [Bid Evaluation]
Post Qual = [Post Qual]
Contract Signing = [Contract Signing]